## Sheet1
Issue ID | Product | Issue Raised Date | Issue Type | Issue Details | Issue Severity | Expected Resolution Date | On-Hold | Issue Resolved Date | Project Stage | Owner | Comments ClearTax | Comments Customer | Company Code/Name | Sample Document ID | Jira ID | RCA Required | Root Cause | Root Cause Category | Add-on Change Required?
1 | EINV | 2025-01-02 | Issue | Ack No was getting added in the excel sheet with decimal values | Low |  | Closed | 2025-01-02 | UAT
2 | EINV | 2025-01-03 | Issue | Date format is incorrect in the excel sheet | Medium |  | Closed | 2025-01-03 | UAT
3 | EINV | 2025-01-04 | Query | If file name is same the the old file name needs to be updated as _1. | Low |  | Closed | 2025-01-04 | UAT
4 | EINV | 2025-01-06 | Bug | Update the code to handle the exception where the buyer details are missing. | High |  | Closed | 2025-01-06 | UAT
5 | EINV | 2025-02-10 | Query | Updating the code handel if the buyer GSTIN is invalid. | High |  | Closed | 2025-02-13 | UAT
6 | EINV | 2025-02-10 | Query | PDF template to be updated. | Medium |  | Closed | 2025-02-13 | UAT
7 | EINV | 2025-02-15 | Query | Email body text to be updated which needs to be sent to the customers. | Medium |  | Closed | 2025-02-15 | UAT
8 | EINV | 2025-02-21 | Query | CC email id to be update while sending the mail using smtp. | Low |  | Closed | 2025-02-21 | UAT
9 | EINV | 2025-02-24 | Query | Adding ERROR_MESSAGE columns in the excel sheet | Medium |  | Closed | 2025-02-24 | UAT
10 | EINV | 2025-02-26 | Query | Multimple mails need to be sent using the smpt email. | High |  | Closed | 2025-02-26 | UAT
11 | EINV | 2025-03-06 | Bug | The annexture file is not getting sent over mail | High |  | Closed | 2025-03-06 | PGLS |  | The annexture file was not added as an input.
12 | EINV | 2025-04-14 | Bug | Afetr generating a few EINV the process got stucked | High |  | Closed | 2025-04-14 | PGLS |  | There was a service glitche from the linux system due to which the service got stucked.